How to Use the

Willowbrook Submittal Review Skill

A plain-English guide for Willowbrook project managers

What this tool actually does

You drag a submittal at it — either a single PDF or the whole Procore export folder — and it does three things before the architect ever sees it:

Checks the submittal against a detailed per-trade checklist (Weston's guide) so nothing obvious is missing.

Compares it to the actual project spec book and cites specific paragraphs the submittal passes or fails against.

Flags known patterns from 500 real submittals on 0309A — things like "operable partitions historically need to be routed to the steel fabricator."

You get two outputs every time:

A short summary printed on your screen (scan in 60 seconds).

A full Word checklist saved next to the submittal — branded, marked DRAFT, ready to hand to the architect or send back to the sub.

Bottom line:  Before every submittal leaves your desk, you run it through this. It takes 30 seconds and catches the stuff you'd otherwise miss at 4:55 on a Friday.

First-time setup (do this once, takes 10 minutes)

You'll do four small things. Ask Weston or IT for help on any of them — none of this is stuff you need to know how to do.

1.  Install Claude Code

If you don't already have it, download from claude.ai/download and install. Sign in with your Willowbrook account.

2.  Install Python (if it's not already there)

Open the Start menu, type "cmd", open the Command Prompt. Type:

python --version

If you see a version number (like "Python 3.12.x"), you're good. If you get "'python' is not recognized", install from python.org/downloads — pick the box that says "Add Python to PATH" during install.

3.  Install the three small Python helpers the skill uses

In Command Prompt, paste this and hit Enter:

pip install pymupdf python-docx pypdf

You'll see a bunch of green text scroll by. When the prompt comes back (a blinking cursor on a new line), you're done. It doesn't matter what folder the command prompt is in — pip installs to Python, not to a folder.

4.  Drop the skill into your Claude folder

The skill lives in a folder called willowbrook-submittal-review. Copy that whole folder into:

C:\Users\<your name>\.claude\skills\

That .claude folder already exists if you've opened Claude Code before. If not, it'll create itself the first time you run Claude. Restart Claude Code after dropping the folder in.

Weston will share the skill folder on SharePoint:  \\willowbrook\shared\Claudes Folder\skills\willowbrook-submittal-review\  Just copy-paste that whole folder into your .claude/skills/ folder.

How to use it — the 30-second version

Open Claude Code. Type one of these two things:

Option A — Natural language (easiest)

Review this submittal: "C:\Users\<you>\Downloads\157_1_Operable Partitions"
Spec book: "C:\Users\<you>\SharePoint\0309A\Spec Book"

You can drag the submittal folder from File Explorer straight into the Claude window — it'll paste the path for you. Same with the spec book folder.

Option B — Slash command (faster once you get used to it)

/review-submittal "C:\...\157_1_Operable Partitions" --spec "C:\...\0309A\Spec Book"

That's it. Claude takes 30–60 seconds and gives you back the review.

What files to point it at

The submittal

Option 1 — a single PDF of the submittal (works fine).

Option 2 — the whole Procore / Fieldwire folder for that submittal (better — it has the cover sheet + all attachments).

The skill figures out which kind you gave it automatically.

The spec book (optional but highly recommended)

Point it at the project's Spec Book folder on SharePoint — something like C:\Users\<you>\SharePoint\0309A - Stillwater HS\Specifications\

Or point it at the raw spec-book PDF directly — it'll split it up by section the first time (takes a minute or two), then cache it so every run after that is instant.

Without the spec book loaded,  the skill can only run the generic checklist. With the spec book loaded, it cites the exact paragraph that a missing item violates — which is what gets it through architect review cleanly. Spend the extra 2 seconds pointing at the spec folder.

Understanding what you get back

The on-screen summary

About 15 lines. It tells you:

Overall status — PASS, CONDITIONAL, FAIL, or INSUFFICIENT_DATA.

What the skill recommends the architect response should be.

The specific items that failed or need your judgment.

Any historical pattern flags (things that burned us before).

One directive sentence telling you what to do next.

The Word checklist

Saved in a review/ folder right next to the submittal. Opens in Word, looks like a branded Willowbrook doc, stamped DRAFT at the top.

It contains:

The full per-trade conformance checklist with pass/fail/warn marks.

Spec paragraph citations for every finding (when the spec is loaded).

Historical pattern flags with the language to copy into your notes.

A draft pushback paragraph if you need to send it back to the sub — just copy, edit, paste into email / Fieldwire / Procore.

Suggested redline callouts for marking up the returned PDF.

The JSON file

Same folder as the Word doc. Not for you — it's for Willow to ingest later. Ignore it, but don't delete it if you're doing a run log for IT.

What the statuses mean

PASS (green)

Every required item was found AND cited against the spec. Recommended response to architect: Approved. Forward it.

CONDITIONAL (gold)

Most items check out, but a few are flagged as warnings or need your judgment. Recommended response: Approved as Noted. Read the warnings, confirm they're acceptable, then forward.

FAIL (red)

Something substantive is missing or wrong. Recommended response: Revise and Resubmit. Use the draft pushback language to send it back to the sub before the architect sees it.

INSUFFICIENT_DATA (gray)

The skill couldn't evaluate enough of the checklist with high confidence — usually because the submittal came in as a scanned image instead of a text PDF. Review it manually. Tell Weston which submittal did this so we can improve the parser.

Three things the skill will NOT do (by design)

Send anything, anywhere. Every output is DRAFT. You are the publish button — it's always you that forwards to the architect, always you that sends pushback to the sub.

Make the final decision on Approved vs. Approved as Noted. It recommends; you decide.

Review RFIs, change orders, bid leveling, sub qualification, or cost analysis. Different tools for different jobs.

If something doesn't work

Claude doesn't respond to "review this submittal"

Did you restart Claude Code after dropping the skill folder in?

Is the folder in ~/.claude/skills/ and named exactly willowbrook-submittal-review (no extra characters)?

"Missing dependency: pymupdf" (or python-docx or pypdf)

Run pip install pymupdf python-docx pypdf in Command Prompt again. Watch for errors in the output — if pip can't install, your Python install is probably the issue, not the skill.

The skill says INSUFFICIENT_DATA

The submittal is probably a scanned image PDF. You'll need to review it manually, or re-request a text-based PDF from the sub.

Tell Weston — if it happens a lot, the next version can add OCR.

The spec book extraction is taking forever

First time only, for a big spec book it can take 5+ minutes. Every run after that reads from the cache and is instant.

If it's been more than 15 minutes, kill it and let Weston know.

The Word doc doesn't match the Willowbrook brand

The skill calls a separate brand skill to apply formatting. If that's not installed, you'll get a plainer version — still usable, just not branded. Ask Weston to share the willowbrook-brand-262 skill too.

Quick reference card

Tape this to your monitor:

One-time setup:
  pip install pymupdf python-docx pypdf
  Drop willowbrook-submittal-review/ into ~/.claude/skills/
  Restart Claude Code

Every submittal:
  "Review this submittal: <folder>   Spec book: <spec folder>"
  (Or drag the folders in — Claude reads them either way)

Reading the result:
  PASS         -> forward to architect
  CONDITIONAL  -> address warnings, then forward
  FAIL         -> copy pushback draft, send to sub first
  INSUFFICIENT -> review manually, tell Weston

All outputs are DRAFT. You are the publish button.

Willowbrook Construction Services  |  Submittal Review Skill v1.1  |  PM Quick-Start Guide

Questions, issues, or suggestions: talk to Weston. Feedback makes v1.2 better.